## Days_1_30_Build_v10
DAILY PREP PLAN v10 — FOREMAN INDUSTRY (50-user blueprint) ¦ 14 Sep → 13 Oct 2026 ¦ BASIC → 1 YOE ¦ SLOT 4 = 18:00–22:00
DESIGN: Aligned to FOREMAN_INDUSTRY_BLUEPRINT_50_USERS Rev3. Slot 1 = unbreakable fundamentals. Slot 2 = Phase A base Foreman (auth refresh Day 3-4, OwnedRepo Day 5, Redis Day 25, demo gate Day 26, Checkpoint 4 + D-01 drill Day 30). Buffer days 7/14/23/30 = recall + checkpoint only. Never cut ownership isolation or approval UI.
SLOT 4 LEARNING TRACK: Days 1–3 System Design finish. Days 4–8 Docker. Days 9–18 AWS core (IAM/ECR/App Runner/Secrets/S3/VPC/CloudWatch). Days 19–21 light K8s. Days 22–30 revision + weak spots + STAR. Always connect infra back to Foreman. Basics ≥4/5 before advancing. Phase A ends Day 30; Phase B starts after.
Date | Day | Weekday | Status | SLOT 1 (10–12) Fundamentals (Basic→1YOE) | Core Interview Topics | Resources | SLOT 2 (12:45–15:45) Foreman Build | SLOT 3 (16:15–17:45) Interview Practice | SLOT 4A (18:00–19:30) Existing Deep Topic | SLOT 4B (20:30–22:00) System Design / Docker / AWS / K8s | Deliverable (must run) | Interview talking point | Daily win
14-Sep-2026 | 1 | Monday | Not Started | 10:00–10:50 — Class vs instance + self + __init__ (IMPLEMENT – BASIC) • Class = blueprint; instance = concrete object with own state • self is explicit in Python (no implicit this) • __init__ initialises state; object already exists before it runs • Write 2 small classes from scratch; instantiate; print id() 10:50–11:40 — Encapsulation + name mangling (IMPLEMENT – BASIC) • Leading __ triggers name mangling (_Class__attr) • Not true privacy — signals "internal" • Why it exists: prevent accidental overwrite in subclasses • Demo with a class that mangles a key; show dir() 11:40–12:00 — Active recall both clusters (score ≥4/5) • Explain both out loud without notes | class vs instance self + __init__ Encapsulation & name mangling Why not true privacy | Python docs: Classes Real Python OOP PEP 8 naming | FOREMAN Day 1: Runnable skeleton + ownership discipline MODE: DELEGATED (Dockerfile, compose, pyproject) + WRITE-THEN-REVIEW (app/main.py) • FastAPI + GET /health + GET /ready • docker-compose: app + db (pgvector-ready) • .env.example • Folders: app/agents llm/ tools/ api/ models/ db/ auth/ approvals/ • Every future table will carry user_id; plan OwnedRepo choke point Deliverable: compose up; /health 200; /docs reachable | 16:15–16:45 Explain-out-loud: class vs instance + encapsulation (record) 16:45–17:15 Live coding: class with __init__, property, __repr__ (15 min) 17:15–17:45 Applications: 2 Tier-3 roles + tracker | ML fundamentals (UNDERSTAND) • Supervised / unsupervised / RL • Overfitting vs underfitting + bias-variance • Why simple models often win • Train/val/test purpose | SYSTEM DESIGN (finish remaining) • Scalability basics • Load balancer types • CAP theorem simple explanation | compose up; /health 200; /docs reachable | "Every table will carry user_id and every read will go through an owner-scoped repository — isolation is designed in from Day 1." | Repo skeleton exists; ownership discipline stated; first OOP cluster explainable
15-Sep-2026 | 2 | Tuesday | Not Started | 10:00–10:50 — Inheritance + super() (IMPLEMENT – BASIC) • is-a relationship; super() calls parent implementation • Method Resolution Order concept (high level only — no C3 deep dive) • Write parent + child; override a method; call super() 10:50–11:40 — Polymorphism + duck typing (IMPLEMENT – BASIC) • Same interface, different behaviour • Duck typing: if it quacks it's a duck — no formal interface required • Write two classes with same method name; pass both to a function 11:40–12:00 — Composition vs inheritance (UNDERSTAND – 1 YOE) • has-a vs is-a • Prefer composition for flexibility (Agent has-a Retriever) • Rule: every answer uses own code, never Animal/Dog | Inheritance + super() Polymorphism & duck typing Composition vs inheritance When to prefer composition | Python docs: Inheritance Real Python Inheritance & Composition | FOREMAN Day 2: Schema + Alembic + CI + ownership columns MODE: WRITE-THEN-REVIEW (models + alembic) + DELEGATED (ci.yml) • users, agents, threads, messages, tool_calls, approvals, usage_logs, documents • Every owned table has user_id + FK + indexes • First isolation test skeleton (user B cannot list user A) Deliverable: migration clean; CI green | 16:15–16:50 Explain inheritance + composition with agent example (record) 16:50–17:20 Live coding: ABC + two implementations (15 min) 17:20–17:45 Applications + tracker | ML evaluation metrics (UNDERSTAND) • Accuracy / Precision / Recall / F1 • When accuracy misleads • Confusion matrix + class imbalance | SYSTEM DESIGN • Database scaling (read replicas, sharding high-level) • Caching strategies overview • CDN role | Migration clean; CI green; ownership columns present | "I prefer composition for agents — has-a retriever so I can swap strategies without touching the agent class. Every query is owner-scoped." | Schema migrated with user_id everywhere; composition explainable
16-Sep-2026 | 3 | Wednesday | Not Started | 10:00–10:50 — Decorators from scratch (IMPLEMENT – BASIC) • Function that takes a function and returns a wrapped function • @wraps to preserve metadata • Write a timing decorator and a simple retry decorator 10:50–11:30 — Generators & yield (IMPLEMENT – BASIC) • Lazy sequences; memory efficiency for large streams • Write a generator that yields chunks from a large string/file 11:30–12:00 — Context managers (IMPLEMENT – BASIC) • __enter__/__exit__ or @contextmanager • Write a timer context manager; use it around a block | Decorators from scratch Generators for streaming Context managers When generators help RAG ingestion | Python docs: Decorators Real Python Decorators primer | FOREMAN Day 3: Registration (bcrypt) + login_attempts table MODE: WRITE-THEN-REVIEW (auth/security.py + routes) • POST /auth/register · bcrypt (cost ≥12) · 409 on duplicate • login_attempts table for lockout (Phase B policy, table now) • Generic error bodies (no user-enumeration) Deliverable: register works; password never plain; duplicate → 409 | 16:15–16:45 Explain decorator + generator + context manager with production reason 16:45–17:15 Live coding: retry-with-backoff decorator (15 min) 17:15–17:45 Applications | Deep Learning conceptual (UNDERSTAND) • Neural net structure plain language • Why transformers replaced RNNs • Fine-tuning vs RAG vs prompting | SYSTEM DESIGN (last day) • Consistency models • Message queues high-level • Wrap-up + notes of key trade-offs | POST /auth/register stores bcrypt; duplicate → 409 | "I use generators when streaming large documents into the chunker so I never hold the whole corpus in memory." | Register works; can write decorator + generator from memory
17-Sep-2026 | 4 | Thursday | Not Started | 10:00–10:45 — Exception hierarchy for tools (IMPLEMENT – BASIC) • Design a small hierarchy for agent tools (ToolError, ValidationError, TimeoutError) • try/except/else/finally patterns 10:45–11:30 — Type hints + dataclasses + Pydantic (IMPLEMENT – BASIC) • When to use dataclass vs Pydantic model • Write a Pydantic model for agent state or tool input with validation 11:30–12:00 — JWT auth flow draw blank (BASIC → 1 YOE) • Draw blank: login → issue token → Bearer header → verify → inject user • Trap: where does revocation fit? | Custom exception hierarchies Pydantic vs dataclasses JWT end-to-end FastAPI Depends | FastAPI Security JWT Pydantic v2 Models JWT.io | FOREMAN Day 4: Access JWT (15m memory) + rotating refresh (httpOnly cookie) MODE: WRITE-THEN-REVIEW (jwt.py + deps.py + sessions) • login issues access JWT + refresh cookie (Path=/auth, Secure, SameSite=Lax) • auth_sessions: token_hash only, family_id, rotate on every refresh • Reuse of rotated token → revoke whole family • Depends injects user; 401 without valid access • CSRF double-submit for refresh/logout Deliverable: full register → login → refresh → protected cycle; family revoke on reuse | 16:15–16:50 Narrate JWT flow blank (record) 16:50–17:20 Live coding: FastAPI endpoint + Pydantic + Depends (15 min) 17:20–17:45 Applications | NLP fundamentals (UNDERSTAND) • What an embedding is • Tokenization (subword / BPE) • Cosine similarity • Context window limits | DOCKER Day 1 – Foundations • What problem Docker solves • Image vs Container • Docker vs VM Video: Nana Docker Crash Course | Login issues JWT + rotating refresh; protected route enforced; reuse revokes family | "Access token lives only in memory (15 min). Refresh is httpOnly rotating cookie; reuse of a rotated token kills the whole family." | Rotating refresh + family revoke works; exception hierarchy designed
18-Sep-2026 | 5 | Friday | Not Started | 10:00–11:00 — FastAPI request lifecycle (IMPLEMENT understanding) • uvicorn → ASGI → middleware stack → DI → route handler → response • Draw the hop sequence blank from memory • Where exceptions are caught relative to middleware 11:00–12:00 — Depends + Pydantic in FastAPI (IMPLEMENT) • Depends() and order of resolution • Write a small endpoint with a Pydantic body + a Depends dependency | FastAPI lifecycle Middleware vs exceptions Depends order Pydantic request/response | FastAPI Dependencies + Middleware Uvicorn concepts | FOREMAN Day 5: Agent CRUD + OwnedRepo choke point MODE: WRITE-THEN-REVIEW (agents routes + models + db/repository.py) • Owner-scoped CRUD via OwnedRepo (no get_by_id without user_id) • unknown tool → 422 • First real isolation tests: B cannot read/list/update A's agents Deliverable: authenticated owner-scoped CRUD; IDOR tests green for agents | 16:15–16:50 Narrate lifecycle blank (record) 16:50–17:20 Live coding: pagination (15 min) 17:20–17:45 Applications | GIL + threading vs multiprocessing vs asyncio (UNDERSTAND) • I/O-bound → asyncio • For LLM calls asyncio is natural fit | DOCKER Day 2 – Commands & Practice • docker run / build / ps / logs / exec • Port binding, volumes basics • Hands-on: run Postgres + your FastAPI locally with Docker | Owner-scoped agent CRUD under JWT; OwnedRepo enforces user_id | "Agents are owner-scoped — every query goes through repository.py which requires user_id. There is no get_by_id without owner." | Agent CRUD live; OwnedRepo choke point in place; lifecycle drawable blank
19-Sep-2026 | 6 | Saturday | Not Started | 10:00–11:00 — Checkpointing concepts (UNDERSTAND – 1 YOE) • What a LangGraph checkpoint row contains • Why Postgres not in-memory for production • Kill-process-and-resume mental model 11:00–12:00 — SQL basics on own tables + indexes + joins (UNDERSTAND) • agents, threads, approvals, usage_logs columns • Inner vs left join examples on own schema • Why indexes matter for approval lookups • +15 min OOP spaced recall | LangGraph checkpoint row Why Postgres checkpointer SQL joins + indexes | LangGraph Persistence docs PostgreSQL CREATE INDEX | FOREMAN Day 6: Checkpointing proven (PostgresSaver) MODE: HAND-TYPED (checkpointer.py) • PostgresSaver · kill process · resume · state matches • Thread status column prepared for later CAS Deliverable: kill + resume works; state correct after restart | 16:15–17:00 Explain checkpoint row + why Postgres (record) 17:00–17:45 Applications (lighter) | Attention & self-attention (UNDERSTAND) • Plain language + temperature / top-p / top-k | DOCKER Day 3 – Dockerfile • Dockerfile instructions • Multi-stage builds concept • .dockerignore • Hands-on: improve Foreman Dockerfile | Kill → resume from Postgres → state correct | "Checkpoints live in Postgres so a process restart doesn't lose the agent's place. Resume reconstructs from the checkpoint." | Kill-and-resume proven; checkpoint explainable
20-Sep-2026 | 7 | Sunday | Not Started | 10:00–11:00 — Week 1 OOP full recall (must be ≥4/5) • 60-second explanation + own-code example for every Tier A concept • Flag any still < 4/5; 10 min targeted fix each 11:00–12:00 — Redraw FastAPI lifecycle + JWT + checkpoint blank • Trap questions: exception location relative to middleware; JWT revocation; what survives kill | Week 1 OOP full set FastAPI lifecycle traps JWT contents Checkpoint kill/resume | Own Build Log Days 1–6 LangGraph checkpoint section | BUFFER DAY — no new build • Absorb overrun • Strengthen HAND-TYPED checkpointer • Who Types What mark • Write Checkpoint 1 talking points • First IDOR matrix rows for agents/threads • Do NOT start Week 2 on unexplained foundation | 16:15–17:45 CHECKPOINT 1 (explain unaided) • JWT contents + rotating refresh + family revoke • Checkpoint row • Why Postgres • Demo: auth + agent CRUD + kill/resume Record. If fails → remediate before Week 2. | Checkpoint 1 remediation OR light ML metric recall • Close gaps only | BUFFER – Docker revision only • Rewrite a clean multi-stage Dockerfile from memory • Explain image layers + caching • No new video | Checkpoint 1 passed unaided OR explicit remediation plan; IDOR skeleton green | "After Week 1 I can explain JWT contents, rotating refresh + family revoke, checkpoint row, and prove kill-and-resume + basic isolation." | Checkpoint 1 done or remediation clear; Week 1 closed honestly
21-Sep-2026 | 8 | Monday | Not Started | 10:00–10:50 — Decorators + generators + context managers recall (IMPLEMENT depth) • Rewrite a timing decorator from memory • Rewrite a file-chunk generator from memory • Explain when each belongs in a RAG/agent pipeline 10:50–11:40 — Exception hierarchy + Pydantic validators (IMPLEMENT) • ToolError hierarchy review • Pydantic model with field validators for tool input 11:40–12:00 — +15 min OOP spaced recall (composition or encapsulation) | Decorators in AI middleware Generators for streaming Pydantic validation Custom exceptions | Pydantic Validators functools.wraps | FOREMAN Day 8: Gateway interface + OpenAI adapter + 25-30 eval cases MODE: HAND-TYPED • Thin gateway interface so providers are swappable • Mocked tests green Deliverable: gateway + OpenAI adapter + eval set; mocked tests green | Explain gateway design why hand-written (record) Live coding: exponential backoff decorator Applications Tier 2 | Hybrid search + RRF + re-ranking (IMPLEMENT) Write minimal fusion function | DOCKER Day 4 – Compose & Best Practices • docker-compose.yml structure • Services, networks, volumes • Common interview Qs (CMD vs ENTRYPOINT) | Gateway + OpenAI adapter + eval set; mocked tests green | "The gateway is a thin interface so I can swap providers without touching the graph." | Gateway + adapter + eval set exist
22-Sep-2026 | 9 | Tuesday | Not Started | 10:00–11:00 — Async vs sync for LLM calls (UNDERSTAND) • Why asyncio fits I/O-bound LLM HTTP calls • When threads still appear (legacy SDKs) • Event loop mental model in one paragraph 11:00–12:00 — Gateway fallback design review (UNDERSTAND) • Primary → secondary on which exceptions? • What must NOT be retried (4xx validation errors) • +15 min OOP recall | Asyncio for LLM calls Provider fallback What not to retry | Python asyncio docs Provider error codes | FOREMAN Day 9: Anthropic adapter + router + fallback MODE: HAND-TYPED • primary raise → fallback once • Error classification (what not to retry) Deliverable: Router falls back once; adapters share interface | Explain fallback + error classification Live coding: custom exception hierarchy Applications | Agentic RAG (IMPLEMENT) + Self-RAG/CRAG (AWARE) | AWS Day 1 – Cloud + IAM • What is Cloud / Regions / AZs • IAM users, roles, policies, least privilege • Hands-on: create IAM role for App Runner style service | Router falls back once; adapters share interface | "When primary is down the router fails over — graph doesn't care which provider answered." | Fallback works; Agentic RAG concept clear
23-Sep-2026 | 10 | Wednesday | Not Started | 10:00–11:00 — Cost metering concepts (UNDERSTAND) • Where cost goes in an agent system: retries, long context, loops, wrong model tier • Per-request vs per-user attribution • usage_logs schema fields you need 11:00–12:00 — Token accounting accuracy (UNDERSTAND) • Prompt tokens vs completion tokens • Why estimates differ from provider bills • +15 min OOP recall | LLM cost drivers Per-request metering usage_logs schema | tiktoken / Anthropic token docs Langfuse cost concepts | FOREMAN Day 10: Cost metering (usage_logs) MODE: HAND-TYPED metering hook • Every gateway call writes usage_logs (tokens + estimated cost) • Prepares for later usage_daily rollup (Phase B) Deliverable: every LLM call writes usage_logs | Scenario: Token spend tripled overnight (record process) Applications | Ragas + LLM-as-judge (UNDERSTAND) + GraphRAG AWARE | AWS Day 2 – Compute & ECR • EC2 basics • ECR: push/pull images • App Runner vs ECS vs Lambda (when to choose which) | Every LLM call writes usage_logs | "I meter per request at the gateway so cost is attributable even on retries." | Metering live; cost-spike process practiced
24-Sep-2026 | 11 | Thursday | Not Started | 10:00–11:00 — SQL deeper: transactions, N+1, EXPLAIN (UNDERSTAND) • BEGIN/COMMIT/ROLLBACK mental model • N+1: how it appears and how to spot it • EXPLAIN basics — sequential scan vs index 11:00–12:00 — Workflow Traces: RAG ingestion path + RAG query path (UNDERSTAND) • Draw both blank from memory • Trap: document updates and deletions strategy • +15 min OOP recall | Transactions + isolation N+1 EXPLAIN RAG paths | PostgreSQL EXPLAIN SQLAlchemy N+1 pgvector | FOREMAN Day 11: pgvector + documents + ingestion (user_id filtered) MODE: HAND-TYPED rag_tool core • documents + chunks with user_id • RAG tool SQL always filters by user_id from auth context (never prompt-only) • 3 test queries return relevant chunks for owner only Deliverable: pgvector search works for 3 queries; B cannot retrieve A's chunks | Narrate RAG paths blank Live coding: chunking + overlap Applications | Hallucination diagnostic (retrieval vs generation) – high frequency Q | AWS Day 3 – Networking light • VPC mental model • Security Groups vs NACL high-level • Why App Runner simplifies networking | pgvector search works for 3 queries; RAG isolation by SQL | "When answer is wrong I first check if retrieved chunks contain the fact. The tenant filter is in the SQL, not the prompt." | pgvector works; hallucination diagnostic solid; RAG isolation proven
25-Sep-2026 | 12 | Friday | Not Started | 10:00–11:00 — Retrieval quality levers (UNDERSTAND) • top-k, score threshold, hybrid weight, re-rank depth • How you'd measure improvement on a small eval set 11:00–12:00 — Chunking strategy comparison (UNDERSTAND) • Fixed, recursive, semantic — trade-offs • Overlap purpose • +15 min OOP recall | top-k, threshold, hybrid, re-rank Chunking trade-offs | LangChain text splitters Ragas context metrics | FOREMAN Day 12: Retrieval quality tuning MODE: HAND-TYPED • top-k, threshold, hybrid, re-rank notes • Measurable hit-rate on small eval set Deliverable: Retrieval tuned with notes | Explain hybrid + RRF + when re-rank Applications (lighter) | Cloud: IAM + Secrets Manager concepts | AWS Day 4 – Storage & Secrets • S3 basics + use cases • Secrets Manager vs Parameter Store vs .env • How your service should fetch LLM keys at runtime | Retrieval tuned with notes | "I treat retrieval quality as measurable — I keep a small eval set." | Retrieval tuned; IAM/Secrets clear
26-Sep-2026 | 13 | Saturday | Not Started | 10:00–11:00 — Tool registry + sensitive flag (UNDERSTAND) • Why enforcement is in code, not the prompt • What "sensitive" means for send_email vs search 11:00–12:00 — Threat model for a tool-executing agent (UNDERSTAND) • Prompt injection via tool results • Approval bypass risks • +15 min OOP recall | Sensitive flag in code not prompt Prompt injection via tool results Approval bypass | OWASP LLM Top 10 LangGraph HITL | FOREMAN Day 13: Tool registry + sensitive flag (code, not prompt) MODE: HAND-TYPED • registry + sensitive flag in code • send_email mocked; allowlist enforced after model output • Prompt-injection via tool results cannot expand allowlist Deliverable: registry + sensitive flag; send_email mocked; unknown tool refused | Explain why sensitive is code flag Applications + Profile Claim Defense | Cloud: ECR + App Runner concepts | AWS Day 5 – Observability + Deploy mental model • CloudWatch logs & metrics basics • How you would debug a slow endpoint using CloudWatch • Full deploy flow: build → ECR → App Runner | Registry + sensitive flag done; allowlist code-enforced | "Sensitive actions are gated by a code flag, not by hoping the model obeys a prompt. Allowlist is intersected after generation." | Registry done; App Runner chosen
27-Sep-2026 | 14 | Sunday | Not Started | 10:00–11:00 — Week 2 full recall (IMPLEMENT/UNDERSTAND depth) • Gateway interface, both adapters, router, metering • RAG tool + hybrid + sensitive flag • Redraw RAG paths + fallback path blank 11:00–12:00 — Trap questions drill • What happens on provider outage? • How does search_knowledge_base become a similarity search? • Why is send_email mocked and how do you say that honestly? | Gateway + fallback + metering Hybrid + sensitive flag Retrieval vs generation | Own Build Log 8–13 | BUFFER DAY — no new build Strengthen HAND-TYPED gateway/router/rag_tool Prepare Checkpoint 2 talking points IDOR matrix extended to documents/approvals | CHECKPOINT 2 (explain unaided) Routing, outage behaviour, how search becomes similarity search Demo: fallback + both tools | Checkpoint 2 remediation OR light ReAct overview | BUFFER – AWS revision • Redraw: IAM role → ECR → App Runner → Secrets → CloudWatch • Explain least-privilege for your agent service • No new content | Checkpoint 2 passed or remediation plan | "After Week 2 I can explain routing, fallback, metering and RAG tool with SQL isolation." | Checkpoint 2 done; Week 2 closed
28-Sep-2026 | 15 | Monday | Not Started | 10:00–11:00 — LangGraph state + TypedDict/Pydantic state (IMPLEMENT understanding) • What fields belong in state vs config • Reducers concept (how partial updates merge) • Draw state shape for Foreman 11:00–12:00 — Graph skeleton mental model (UNDERSTAND) • StateGraph, entry point, compile with checkpointer • +15 min OOP recall (ABC or composition) | AgentState design Reducers StateGraph + checkpointer | LangGraph StateGraph + Persistence docs | FOREMAN Day 15: AgentState + graph skeleton MODE: HAND-TYPED • TypedDict state + reducers • StateGraph + checkpointer Deliverable: graph compiles; empty invoke returns | Explain AgentState fields Live coding: node that updates state Applications | ReAct loop · agent vs chain · tool calling (IMPLEMENT) | AWS Day 6 – Practice & Interview Qs • Common 1 YOE AWS questions • “How would you deploy this agent platform?” • Cost awareness | Graph compiles with checkpointer | "State is a TypedDict the graph passes between nodes — every node returns a partial update." | Graph skeleton compiles; ReAct explainable
29-Sep-2026 | 16 | Tuesday | Not Started | 10:00–11:00 — agent_node responsibilities (UNDERSTAND) • Call gateway with current messages • Parse tool calls vs final answer • What it must NOT do (execute tools itself) 11:00–12:00 — Message history shape in state (UNDERSTAND) • Roles, tool_call_id, tool results • +15 min OOP recall | agent_node design Tool call parsing vs final answer Separation decide vs execute | LangGraph Tool calling OpenAI function calling | FOREMAN Day 16: agent_node MODE: HAND-TYPED • agent_node is the only place the LLM is called • Parses tool calls vs final answer Deliverable: agent_node runs against mocked gateway | Explain agent_node step-by-step Live coding under timer Applications | Agent memory types + planning + reflection | AWS Day 7 – Consolidation • Write 1-page architecture of your AWS footprint • Trade-offs: App Runner vs ECS • What breaks first at higher traffic | agent_node updates state correctly | "The agent node is the only place the LLM is called — it either finishes or requests a tool." | agent_node works; memory types clear
30-Sep-2026 | 17 | Wednesday | Not Started | 10:00–11:00 — Conditional routing edges (IMPLEMENT understanding) • Routing function signature: state → next node name • Pure function of state — no side effects • How to test every branch without LLM 11:00–12:00 — Edge cases in routing (UNDERSTAND) • Missing tool name · malformed tool call · empty response • +15 min OOP recall | Routing as pure function of state Testing branches without LLM | LangGraph Conditional edges | FOREMAN Day 17: Conditional routing MODE: HAND-TYPED • Routing as pure function of state • final→END, non-sensitive→tool, sensitive→approval Deliverable: All three routing branches work | Draw + narrate routing blank Live coding: pure routing function + tests Applications | Failure modes: loops, tool misuse, context overflow | AWS Day 8 – Weak spots + hands-on • Any remaining weak AWS topic • Rehearse deploy story for Checkpoint 4 | All three routing branches work | "Routing is a pure function of state — no hidden side effects." | Routing works; failure modes named
01-Oct-2026 | 18 | Thursday | Not Started | 10:00–11:00 — Tool call round-trip trace (draw blank) • agent_node → route → tool_node → observation → back to agent_node • Where sensitive flag is checked 11:00–12:00 — Tool node error handling (UNDERSTAND) • Tool raises · timeout · invalid args • What gets written to state on failure • +15 min OOP recall | Tool round-trip Sensitive flag check point Observation format | LangGraph ToolNode + error handling | FOREMAN Day 18: tool_node MODE: HAND-TYPED • non-sensitive executes; sensitive does not auto-run • Dispatch by name from registry; unknown → typed refusal Deliverable: tool_node respects sensitive flag | Narrate tool round-trip blank Live coding: dispatch by name from registry Applications | Multi-agent patterns AWARE + CrewAI comparison | AWS Day 9 – Final AWS polish • Rapid fire: IAM, ECR, Secrets, App Runner, CloudWatch • Link everything back to Foreman ADRs | tool_node respects sensitive flag | "The tool node never executes a sensitive tool on its own." | tool_node respects flag; CrewAI comparison written
02-Oct-2026 | 19 | Friday | Not Started | 10:00–11:00 — Loop protection design (UNDERSTAND) • Max iterations in state • Repeated (tool, args) detection • Safe abort terminal state 11:00–12:00 — Workflow Trace: agent invocation E2E so far (draw blank) • Auth → invoke → agent_node → route → tool_node → ... • +15 min OOP recall | Iteration cap Repeated tool detection Safe terminal states | LangGraph recursion limits | FOREMAN Day 19: Loop protection + approvals additive columns MODE: HAND-TYPED • Iteration cap in state • approvals: decided_at, executed_at (for once-only) Deliverable: Iteration cap works; approvals schema ready for CAS | Scenario: agent stuck in tool-call loop Applications | HITL deep dive: interrupt() semantics (critical) | KUBERNETES Light Day 1 • Why K8s exists • Pod, Node, Cluster • Deployment vs Pod | Iteration cap works | "Loop protection is a hard cap in state — a runaway agent always stops." | Loop protection works; HITL semantics clear
03-Oct-2026 | 20 | Saturday | Not Started | 10:00–11:00 — interrupt() and checkpoint interaction (UNDERSTAND) • What exactly gets written on interrupt • Thread / run identity for resume 11:00–12:00 — Workflow Trace: HITL interrupt → approval → resume (draw blank) • Trap: approval bypass; expired approval; concurrent resumes • +15 min OOP recall | interrupt() contents Resume identity Approval bypass risks | LangGraph HITL + Interrupt docs | FOREMAN Day 20: human_approval_node + interrupt() + thread CAS MODE: HAND-TYPED • sensitive path: interrupt → approvals row → thread status=waiting_approval • Thread CAS: idle → running (basic); 409 if busy • interrupt() pauses and persists; resume reconstructs Deliverable: sensitive path pauses; approval row exists; resumable; CAS prevents double-run | Explain interrupt() and what is stored Applications | Guardrails overview (prompt injection, rate limits, audit) | KUBERNETES Light Day 2 • Service (ClusterIP / NodePort concept) • Desired state vs actual state • Basic kubectl mental model | interrupt + pending approval works; thread CAS basic | "interrupt() pauses the graph and persists state — resume reconstructs from checkpoint. Thread status CAS prevents concurrent runs." | HITL interrupt path works; CAS in place
04-Oct-2026 | 21 | Sunday | Not Started | 10:00–11:00 — Resume path mental model (UNDERSTAND) • Approve vs reject paths • Why resume reconstructs from checkpoint not original request 11:00–12:00 — Partial failure handling (UNDERSTAND) • Idempotent resume • Safe terminal states • +15 min OOP recall | Approve vs reject Idempotent resume Safe terminal states | LangGraph Resume docs | FOREMAN Day 21: Resume path (approve + reject) + execute-once MODE: HAND-TYPED • both paths complete from stored checkpoint • Atomic UPDATE approvals SET status=… WHERE status='pending' • executed_at set in same transaction as tool execution • Owner + run_id re-checked on resume Deliverable: Approve and reject both work; no double execution | Narrate pause→approve→resume and pause→reject (timed) Applications | Production reliability scenarios (provider down, rate limit, DB pool) | KUBERNETES Light Day 3 + Comparison • Why you chose App Runner instead of EKS • When you would move to K8s later • 5 interview questions practice | Approve and reject both work; execute-once proven | "Resume loads the checkpoint and continues — original request is long gone. Approval is atomic and executes at most once." | Both resume paths work
05-Oct-2026 | 22 | Monday | Not Started | 10:00–11:00 — Full agentic recall (all nodes/edges) (IMPLEMENT depth) • Walk every node and edge from memory • Three paths: auto / approve / reject 11:00–12:00 — Integration test strategy (UNDERSTAND) • How to test the three paths without real LLM spend • What the critical-path tests must prove | Full topology Three paths: auto / approve / reject | LangGraph Testing docs | FOREMAN Day 22: Full loop integration test (three paths) MODE: HAND-TYPED tests • auto / approve / reject paths green • Integration tests against real PG Deliverable: Three-path integration green | Explain full vertical slice in 3 min (record) Applications | Framework comparison (LangGraph vs CrewAI vs AutoGen vs raw loop) | REVISION – Docker + AWS + K8s • 20 min Docker flash cards • 30 min AWS architecture redraw • 20 min K8s core objects • Weak spots only | Three-path integration green | "I can demonstrate auto, approve, and reject paths from the same graph." | Three-path green; framework trade-off written
06-Oct-2026 | 23 | Tuesday | Not Started | 10:00–11:00 — Week 3 full recall (IMPLEMENT/UNDERSTAND depth) • Full graph + interrupt + resume + loop protection • Redraw all Workflow Traces blank 11:00–12:00 — Checkpoint 3 trap questions • What interrupt() actually persists • Why resume from checkpoint (not original request) • How execute-once is enforced | Full graph + interrupt + resume + loop protection | Own graph.py + resume.py | BUFFER DAY — no new build Strengthen HAND-TYPED graph/nodes/resume Prepare Checkpoint 3 talking points Extend IDOR matrix + approval race test skeleton | CHECKPOINT 3 (explain unaided) Every node/edge · interrupt() · why resume from checkpoint Demo: pause → approve → resume → complete via API | Checkpoint 3 remediation OR ADR review | BUFFER – Full infra revision • Explain entire deploy path from zero • Docker → ECR → App Runner → Secrets → observability • Prepare Checkpoint talking points | Checkpoint 3 passed or remediation plan | "After Week 3 I can walk every node and edge and prove pause-approve-resume + execute-once." | Checkpoint 3 done; Week 3 closed
07-Oct-2026 | 24 | Wednesday | Not Started | 10:00–11:00 — Observability concepts (UNDERSTAND) • Traces vs logs vs metrics — when you use each • Langfuse for agent runs (what a full trace shows) 11:00–12:00 — Latency diagnostic structure (UNDERSTAND) • Breakdown: network → LLM → retrieval → tool → DB • How you'd investigate RAG 400ms → 4s | Traces vs logs vs metrics Langfuse for agent runs Latency breakdown | Langfuse docs | FOREMAN Day 24: Langfuse call sites + request_id MODE: DELEGATED client + HAND-TYPED call sites • full invoke produces visible Langfuse trace • request_id / user_id / thread_id correlation Deliverable: Langfuse full trace visible | Scenario: RAG 400ms → 4s investigate Applications | Cloud: IAM, ECR, App Runner, Secrets (prepare for deploy) | Infra + Observability link • How Langfuse + CloudWatch fit together • Debugging flow for latency / cost spike using both | Langfuse full trace visible | "Every LLM and tool call is traced — when something is slow I look at the trace first." | Tracing live; deploy concepts ready
08-Oct-2026 | 25 | Thursday | Not Started | 10:00–11:00 — Prompt injection defenses (UNDERSTAND) • Injection via tool results • Delimiting + allow-lists (code enforcement, not prompt) 11:00–12:00 — Rate limiting + CORS + secrets hygiene (UNDERSTAND) • Rate limit as both safety and cost control • CORS basics for the approval UI • No secrets in image / repo — Secrets Manager pattern | Injection via tool results Delimiting Rate limit + CORS + no secrets in image | OWASP LLM Top 10 FastAPI CORS AWS Secrets Manager | FOREMAN Day 25: Redis limiter (fail-closed) + CORS + secrets + structured errors + flags + idempotency MODE: HAND-TYPED + DELEGATED Redis • Upstash Redis: rate limits, invoke concurrency counters (thin version) • Fail-closed: login/register/invoke → 503 limiter_unavailable if Redis down • problem+json structured errors with stable codes • feature_flags table + INVOKES_ENABLED kill switch (no redeploy) • idempotency_keys for invoke and approval decision • Rate limit, CORS, secrets audit, delimiting Deliverable: 429 works; secrets audit clean; Redis fail-closed; kill switch flips without redeploy | Scenario: Token spend tripled Applications | Responsible AI checklist applied to Foreman | Security & Secrets deep • Secrets never in image/repo • IAM least privilege for the service role • Rate limiting + CORS as part of security story | 429 + secrets clean + Redis fail-closed + kill switch + idempotency | "Rate limits protect cost and abuse; Redis is fail-closed on login and invoke because the limiter is the only brake. Kill switch is a flag, not a redeploy." | Security + limiter baseline in place
09-Oct-2026 | 26 | Friday | Not Started | 10:00–11:00 — Docker build vs run + multi-stage + healthcheck (UNDERSTAND) • Image vs container; layers and caching • Multi-stage: why builder stage is discarded • HEALTHCHECK purpose for App Runner / orchestrators 11:00–12:00 — Test gap analysis (UNDERSTAND) • Critical-path coverage vs happy-path only • What the demo-gate and IDOR tests must prove | Docker build vs run Multi-stage Critical path coverage | Docker multi-stage + Healthcheck docs | FOREMAN Day 26: Demo gate form + test gaps + vertical-slice E2E • demo_requests table + public POST /demo-requests (IP rate-limited) • is_owner / is_demo / demo_expires_at on users • Unapproved / expired → 403 demo_required / demo_expired on /invoke (zero provider calls) • Owner-only approve/deny routes (quota-on-approve deferred to Phase B) • Critical-path + E2E green; IDOR/race skeletons expanded Deliverable: critical-path + E2E green; demo form + gate enforced; Mock Interview #1 | Mock Interview #1 (full, with interruptions) Applications | CI/CD pipeline trace (push → lint → test → build → ECR → App Runner) | End-to-end deploy story practice • Narrate full path: local Docker → CI → ECR → App Runner → smoke test • Record yourself (3–4 min) | Critical-path + E2E green; demo gate blocks unapproved invoke | "The public link is open, the spending is not: demo access is approved by hand, time-boxed, and capped. Unapproved visitors never reach the LLM." | Tests solid; demo gate live; Mock #1 done
10-Oct-2026 | 27 | Saturday | Not Started | 10:00–11:00 — Deploy topology + ADR-007/009 recall (UNDERSTAND) • App Runner model (what it abstracts) • Failure domains: compute / state / inference / observability • App Runner vs ECS — why this project chose App Runner 11:00–12:00 — Full architecture redraw blank • From public URL → App Runner → Postgres → LLM providers • Where the demo gate and kill switch sit | App Runner model Failure domains App Runner vs ECS | AWS App Runner docs ADR sheet | FOREMAN Day 27: Frontend A (login, send, display) + staging stand-up MODE: DELEGATED • can login and see non-sensitive response • Staging App Runner + staging Supabase + staging Redis stood up • CUT RULE: never cut approval UI (Day 28) Deliverable: UI login + non-sensitive response visible; staging reachable | Explain full architecture + ADRs from memory Applications + Profile Claim Defense | Migration & upgrade scenarios (state schema change, SDK bump) | Trade-off practice (infra) • App Runner vs ECS vs Lambda vs K8s • Why Postgres checkpointer on same DB • Failure domains (ADR-009) | UI login + non-sensitive response visible; staging up | "The UI is deliberately minimal — the demo that matters is the approval flow. Staging is a real second environment." | Basic UI works; architecture narrative practiced; staging live
11-Oct-2026 | 28 | Sunday | Not Started | 10:00–11:00 — Approval UI requirements (UNDERSTAND) • What the browser must show and what it must call • Resume API contract (approve / reject) • What never to cut in the demo 11:00–12:00 — Full architecture redraw blank (from memory) • Every major component + data flow • Where ownership isolation and sensitive flag are enforced | Approval UI flow Resume API contract What never to cut in demo | Own resume.py + vertical slice | FOREMAN Day 28: Frontend B — APPROVAL UI (never cut) + restore drill prep • from browser approve sensitive action and see run complete • Backup/restore rehearsal notes (pending approval must survive) Deliverable: Approval UI drives real resume end-to-end | Mock Interview #2 or full vertical-slice demo Applications | "What would you do differently now?" 90s answer practice | STAR + Infra stories • Prepare 2 STAR stories involving Docker/AWS decisions • “Tell me about a design decision you made” | Approval UI works; 'do differently' answer drafted | "The approval UI is the demo that proves the architecture. A pending approval must survive process restart and restore." | Approval UI works; restore story prepared
12-Oct-2026 | 29 | Monday | Not Started | 10:00–11:00 — Full architecture + all 9 ADRs from memory (UNDERSTAND depth) • Every decision + the rejected alternative + why • Scale / latency / cost-spike talking points 11:00–12:00 — Checkpoint 4 trap questions • Honest AI-assisted answer (Who Types What) • What is mocked and how you say it • Demo gate bounds spend on the public URL | All 9 ADRs + rejected alternatives Scale / latency / cost spike Honest AI-assisted answer | ADR Trade-offs sheet Who Types What | FOREMAN Day 29: CD + App Runner deploy + smoke + Checkpoint 4 prep MODE: DELEGATED + VERIFY by hand • public URL serves full slice (demo gate on) • Staging smoke: restart service with pending approval → still resumes • Image-tag rollback path documented Deliverable: public URL live; smoke + restart-and-resume proven | CHECKPOINT 4 (explain unaided) Entire architecture + every ADR + demo on public URL | Checkpoint 4 remediation OR STAR #3 polish | Final infra polish for Checkpoint 4 • All ADRs related to deploy + infra • Public URL demo readiness | Public URL live; Checkpoint 4 passed or remediation started | "The system is deployed, observable, and gates irreversible actions behind human approval. Demo gate keeps the public URL from becoming an unbounded bill." | Public URL live; Checkpoint 4 done or clear
13-Oct-2026 | 30 | Tuesday | Not Started | 10:00–11:00 — Day 30 Success Criteria self-audit • Tier A scores, Checkpoint status, Profile claim status • Who Types What filled; no fabricated claims 11:00–12:00 — Final weak-spot patch only • Close only the gaps that block Checkpoint 4 / honesty • No new topics | Day 30 criteria Tier A scores Checkpoint status Profile claim status | Dashboard + Who Types What + STAR sheet | BUFFER / FINAL — no new features • README final + honest framing (§14b honesty table) • Architecture diagrams + ADRs confidence • Who Types What filled • First drill D-01 (IDOR) completed end-to-end: create flaw → ship staging → discover → roll back → fix → regression gate • Day 30 Success Criteria self-audit • No fabricated claims; Phase A closed cleanly | STAR stories finalised (rehearse top 3 timed) Application count check · Month 2 plan | Close intensive phase — light review or rest Note first interview targets | Close Phase 1 – infra checklist • Honest self-score on Docker / AWS / K8s • Note remaining gaps for Phase 2 • Light review only | Day 30 gate reviewed; phase closed cleanly; D-01 drill write-up exists; no fabricated claims | "I spent 30 days building something I can actually defend. Security is practised as create → ship → discover → roll back → fix → gate." | Intensive phase closed; checklist honest; stories ready; first drill done

## Days_31_60_PhaseB_Defense
DAYS 31–60 · PHASE B (Scale & Harden to 50-user) + STRONG DEFENSE ¦ 1 Oct → 30 Oct 2026 ¦ Same slot structure as Days 1–30
GOAL: Finish full Industry Blueprint (Phase A already done in Days 1–30). Phase B adds quotas, concurrency caps, audit_events, hardened CAS, email verify, staging+prod, backup drill, security drills, Checkpoint 5. Every day still has Slot 3 defense practice so you can strongly defend BOTH phases. Depth = Basic→Intermediate + project-relevant.
SLOT STRUCTURE (same as Sheet 1): Slot 1 10–12 Fundamentals/Weak spots ¦ Slot 2 12:45–15:45 Phase B Build ¦ Slot 3 16:15–17:45 Interview Defense (record) ¦ Slot 4A 18:00–19:30 Deep topic ¦ Slot 4B 20:30–22:00 AWS/Security/STAR. Buffer days keep recall + checkpoint only.
Date | Day | Weekday | Status | SLOT 1 (10–12) Fundamentals / Weak spots | Core Interview Topics | Resources | SLOT 2 (12:45–15:45) Phase B Build / Harden | SLOT 3 (16:15–17:45) Interview Defense Practice | SLOT 4A (18:00–19:30) Deep Topic | SLOT 4B (20:30–22:00) AWS / Security / STAR | Deliverable (must run) | Interview talking point | Daily win
1-Oct-2026 | 31 | Thursday | Not Started | 10:00–11:00 — Phase A full recall (auth + OwnedRepo + RAG isolation) (UNDERSTAND depth) • Rotating refresh + family revoke • OwnedRepo choke point (no get_by_id without user_id) • RAG user_id filter is in SQL, not the prompt 11:00–12:00 — Weak spots from Checkpoint 4 • List any topic still < 4/5; targeted fix only | Rotating refresh family revoke OwnedRepo choke point RAG user_id in SQL | Own Build Log Days 1–30 Blueprint §4.4 §5 | PHASE B H1 start: usage_daily table + transactional metering • Create usage_daily (user_id, day, tokens, cost_usd) • Gateway writes usage_logs + usage_daily in one transaction • Nightly reconcile query skeleton Deliverable: every gateway call updates both tables | 16:15–17:00 Record 90s: rotating refresh + family revoke 17:00–17:45 Record 90s: OwnedRepo + why no get_by_id without owner | Cost blast radius arithmetic (50 × $0.50 vs $15 kill switch) | AWS: revisit IAM least privilege for the service role | usage_daily live; dual write works | "I meter at the gateway so even retries are attributed. usage_daily is the O(1) quota check." | Phase B metering foundation live
2-Oct-2026 | 32 | Friday | Not Started | 10:00–11:00 — Async / one-worker / event-loop recall (UNDERSTAND) • Why 1 uvicorn worker + scale instances (not threads for LLM) • Blocking calls inside async path — what breaks 11:00–12:00 — Quota design concepts (UNDERSTAND) • Per-user vs global concurrency caps • Kill switch idea (INVOKES_ENABLED without redeploy) | Async blocking calls Per-user vs global caps Kill switch idea | Blueprint §0.1 §9.1 §8.5 | PHASE B H2: Per-user + global invoke concurrency caps (Redis) • invoke:user:{id} counter (max 2) • global counter (max 10) • 429 + Retry-After when full • Thin version already on Day 25 — harden & test Deliverable: 3rd concurrent invoke from one user → 429; 11th global → 429 | 16:15–17:00 Record: why 1 uvicorn worker + scale instances 17:00–17:45 Scenario: one user tries to own the pool — what happens? | Feature flags table + INVOKES_ENABLED kill switch (already seeded Day 25) — test flip without redeploy | AWS: CloudWatch alarms mental model for cost spike | Per-user + global caps enforced; kill switch flips in <30s | "One user cannot exhaust the pool. Kill switch stops new invokes without a redeploy." | Concurrency caps + kill switch proven
3-Oct-2026 | 33 | Saturday | Not Started | 10:00–11:00 — Decorators / generators / context managers spaced recall (IMPLEMENT depth) • Rewrite timing decorator + chunk generator from memory • When each belongs in RAG/agent pipeline 11:00–12:00 — Structured errors + idempotency concepts (UNDERSTAND) • problem+json with stable codes • Idempotency-Key behaviour (same body → same response; different body → 422) | problem+json stable codes Idempotency-Key behaviour | Blueprint §8.3 §8.4 | PHASE B: Harden structured errors + idempotency store • All 4xx/5xx return problem+json with stable code • idempotency_keys table for invoke + approval decision • Same key + same body → stored response; different body → 422 Deliverable: replayed invoke returns same response, no second graph run | 16:15–17:00 Record 90s: structured error example + why stable codes matter 17:00–17:45 Record: idempotency on approval decision (double-click safe) | Security: OWASP LLM Top 10 mapped to Foreman controls | AWS: Secrets Manager rotation story | Structured errors + idempotency live | "Idempotency-Key stops the mobile retry from double-sending the email." | Idempotency + clean errors done
4-Oct-2026 | 34 | Sunday | Not Started | 10:00–11:30 — Week 5+6 full recall (Python + Schema + RAG) (must be ≥4/5) • Composition, JWT limits, RAG isolation • Own-code examples only 11:30–12:00 — Trap questions on OwnedRepo + user_id SQL • What happens if a route bypasses the repository? • Can prompt injection expand the tenant filter? | Composition JWT limits RAG isolation | Own notes + scorecard | BUFFER / RECALL DAY — no new Phase B features • Strengthen any weak metering / caps tests • Write Checkpoint 5 talking points (draft) • IDOR matrix rows for new quota endpoints | 16:15–17:45 Defense practice: 3× 90s recordings (refresh, OwnedRepo, RAG isolation) Score them honestly | Light: Model Context Protocol (MCP) AWARE only — 20 min | Rest or light STAR | Recall scores ≥4/5 on core Phase A topics | "After Phase A I can defend isolation, refresh families, and RAG tenant filter cold." | Phase A defense solid; ready for more Phase B
5-Oct-2026 | 35 | Monday | Not Started | 10:00–11:00 — FastAPI lifecycle + Depends recall (UNDERSTAND) • Hop sequence blank from memory • Order of Depends resolution 11:00–12:00 — Thread CAS deep dive (UNDERSTAND – 1 YOE) • threads.status machine: idle → running → waiting_approval → idle • CAS with run_id; 409 thread_busy • Why concurrent invoke on same thread must yield exactly one 202 | Thread status machine 409 thread_busy run_id | Blueprint §4.1 §9.3 | PHASE B H3: Harden Thread CAS • threads.status: idle → running → waiting_approval → idle • CAS with run_id • Concurrent invoke on same thread → exactly one 202, one 409 • Resume re-checks run_id + owner Deliverable: two parallel invokes → 1 success, 1×409; no interleaved checkpoints | 16:15–17:00 Record: walk thread CAS + why it exists 17:00–17:45 Live coding style: write the UPDATE … WHERE status='idle' from memory | Approval execute-once + lazy expiry recall | AWS: App Runner max instances = 2 reasoning | Thread CAS hardened and tested | "Thread CAS prevents two graphs from writing checkpoints under the same thread_id." | CAS solid
6-Oct-2026 | 36 | Tuesday | Not Started | 10:00–11:00 — JWT + rotating refresh full defense prep (UNDERSTAND depth) • Access token 15 min in memory only • Refresh is httpOnly rotating cookie; reuse of rotated token kills family • logout-all behaviour 11:00–12:00 — Session list + logout-all (UNDERSTAND) • GET /auth/sessions (owner only) • What still works after stolen access token (and for how long) | Family revoke logout-all behaviour 15-min access window honesty | Blueprint §4.4 §4.6 | PHASE B: Session management polish + lockout policy • GET /auth/sessions (owner only) • DELETE /auth/sessions/{id} • POST /auth/logout-all → revoke every family • Failed-login lockout 5/15 min (table already exists) Deliverable: logout-all kills other devices within one access-token lifetime | 16:15–17:00 Record full auth story (access + refresh + family + logout-all) 17:00–17:45 Trap: stolen access token — what still works and for how long? | Email verification flag (REQUIRE_EMAIL_VERIFY) — design only today | AWS: least-privilege IAM for App Runner task role | Session list + logout-all + lockout live | "Access token lives 15 min in memory only. Refresh family revoke is the real off-switch." | Full auth model defendable
7-Oct-2026 | 37 | Wednesday | Not Started | 10:00–12:00 — CHECKPOINT-style recall: Auth + Caps + CAS + Metering • Continuous walk of rotating refresh, OwnedRepo, concurrency caps, Thread CAS, usage_daily • Score yourself; note any stumble for remediation | All Phase B H1–H3 so far | Own tests + Blueprint | BUFFER + soft gate • Fix any failing tests from H1–H3 • Extend IDOR matrix to quota and session endpoints • Prepare 8-min continuous take covering refresh + caps + CAS | 16:15–17:45 Record one continuous 8–10 min defense of Phase A auth + Phase B caps/CAS Score and note weak spots | Demo gate recall (already built Day 26) | Light revision only | Soft gate passed or remediation list written | "I can now defend the full auth model plus the concurrency and metering controls." | H1–H3 closed
8-Oct-2026 | 38 | Thursday | Not Started | 10:00–11:00 — Schema splits + transactions recall (UNDERSTAND) • Why approvals ≠ tool_calls • BEGIN/COMMIT patterns for dual-write (usage_logs + usage_daily) 11:00–12:00 — audit_events design (UNDERSTAND) • Action vocabulary: auth.*, invoke.*, approval.*, demo.*, flag.*, quota.* • Same transaction as the decision where possible • No secrets or full prompts in metadata | Why approvals ≠ tool_calls Audit action vocabulary | Blueprint §7.2 | PHASE B H4: audit_events table + write on every consequential action • Actions: auth.*, invoke.*, approval.*, demo.*, flag.*, quota.* • Same transaction as the decision where possible • No secrets or full prompts in metadata Deliverable: approve / reject / kill-switch / quota-deny all write audit rows | 16:15–17:00 Record: why audit is required for 50-user claims 17:00–17:45 Walk one audit row from a decision | Security Practice Drill loop introduction (create → ship → discover → rollback → fix) | AWS: CloudWatch Logs Insights basic queries | audit_events live on critical paths | "Every consequential action has an audit row. That is how we reconstruct an incident." | Audit foundation done
9-Oct-2026 | 39 | Friday | Not Started | 10:00–11:00 — N+1 + EXPLAIN recall (UNDERSTAND) • How N+1 appears; sequential scan vs index 11:00–12:00 — Email verification + password reset concepts (UNDERSTAND) • REQUIRE_EMAIL_VERIFY flag (off locally, on staging/prod) • Verification enforced at /invoke, not at login • Reset token table high-level flow | REQUIRE_EMAIL_VERIFY flag Reset flow high-level | Blueprint ADR-021 | PHASE B H5: Email verification gate + password reset skeleton • users.email_verified_at • Flag REQUIRE_EMAIL_VERIFY (off locally, on staging/prod) • /invoke returns 403 email_unverified when flag on and not verified • Password reset token table + basic flow (can stay minimal) Deliverable: unverified user blocked from invoke when flag is on | 16:15–17:00 Record: where verification is enforced and why at /invoke 17:00–17:45 Honesty: what is fully built vs skeleton | Out-of-band approval email adapter (mock only) | AWS: SES or mock email provider decision | Email verify gate works | "Verification is enforced at invoke, not at login, so existing sessions are not surprised." | H5 gate live
10-Oct-2026 | 40 | Saturday | Not Started | 10:00–11:00 — Embeddings + cosine + tenant filter recall (UNDERSTAND) • What an embedding is; cosine in plain language • Tenant filter is in the SQL, never prompt-only 11:00–12:00 — IDOR / race / quota test matrix design (UNDERSTAND) • CI gate tests vs drills • What each integration-* test must prove (zero provider calls on deny) | CI gate tests vs drills | Blueprint §11.2 §10.2 | PHASE B H6 start: Expand CI test matrix • integration-idor (all owned resources) • integration-quota (at-limit → 429 + zero provider calls) • integration-concurrency • integration-race (double approve, concurrent invoke) • integration-demo-gate Deliverable: at least IDOR + quota + concurrency tests green in CI | 16:15–17:00 Record: how I test isolation without calling the real LLM 17:00–17:45 Walk one failing test → fix → gate story | Security drills: pick D-01 (IDOR) and run the full loop on staging | AWS: staging vs prod secret parity checklist | Core CI gates green | "The IDOR and quota tests are release gates, not nice-to-haves." | CI gates strengthened
11-Oct-2026 | 41 | Sunday | Not Started | 10:00–12:00 — Full Phase A + H1–H5 recall + trap questions • Auth, OwnedRepo, RAG isolation, caps, CAS, metering, audit, email-verify • Trap: can an unapproved demo reach the LLM? Can a non-owner approve? | Everything so far | Scorecard + Build Log | BUFFER DAY — no new features • Fix any red tests • Complete D-01 drill write-up • Draft Checkpoint 5 acceptance list | 16:15–17:45 Defense block: record 4× 90s (RAG isolation, CAS, kill switch, demo gate) Honest scoring | Light only | Rest | All critical tests green; drill write-up exists | "I practise security as create → ship → discover → rollback → fix." | Stable base for final Phase B
12-Oct-2026 | 42 | Monday | Not Started | 10:00–11:00 — Testing strategy recall (UNDERSTAND) • Critical-path + IDOR + quota + concurrency + race + demo-gate 11:00–12:00 — Staging vs prod parity (UNDERSTAND) • Distinct DB, Redis, LLM keys, signing keys per env • /ready does real SELECT 1 + Redis PING (not just process up) | Parity rules /ready deep check | Blueprint §11.5 §11.8 | PHASE B H7: Staging + Prod parity + /ready • Distinct DB, Redis, LLM keys, signing keys per env • /ready does real SELECT 1 + Redis PING (200 ms timeout) • Boot log shows resolved hosts (never secrets) • Staging smoke: restart with pending approval → still resumes Deliverable: /ready 503 when Redis or PG down; staging smoke passes | 16:15–17:00 Record: difference between /health and /ready 17:00–17:45 Scenario: Redis down — what returns 503 and what still works? | Sentry integration (best-effort, request_id + user_id tags) | AWS: App Runner staging + prod services side-by-side | /ready deep + staging parity live | "/ready tells the platform the dependencies are actually reachable." | H7 done
13-Oct-2026 | 43 | Tuesday | Not Started | 10:00–11:00 — Retrieval vs generation diagnostic recall (UNDERSTAND) • First check: do retrieved chunks contain the fact? 11:00–12:00 — Backup & restore concepts (UNDERSTAND) • Pending approval must survive restore • Rollback (app image) vs DB restore — when each is used | Pending approval must survive restore | Blueprint §18.6 | PHASE B H8: Backup & restore drill • Supabase backup enabled • Restore most recent backup into scratch project • Point local app at it • Verify a thread that was waiting_approval can still be approved and resumed • Record wall-clock time Deliverable: restore drill completed + timing written in docs/runbooks/ | 16:15–17:00 Record: how long restore actually took and what survived 17:00–17:45 Rollback (app image) vs DB restore — when each is used | Runbook: bill spike + Redis down procedures (write them) | AWS: backup retention and restore permissions | Restore drill done; runbook started | "A pending approval survives both process restart and backup restore." | H8 done
14-Oct-2026 | 44 | Wednesday | Not Started | 10:00–12:00 — Soft gate: H1–H8 + Phase A core • Metering, caps, CAS, audit, /ready, restore, demo gate • List any remaining gaps before Checkpoint 5 prep | All Phase B so far | Own tests + drill write-ups | BUFFER + remediation • Fix any remaining test or drill gaps • Ensure demo gate still blocks unapproved invoke • Prepare Checkpoint 5 evidence list | 16:15–17:45 Long defense recording (12–15 min) covering metering, caps, CAS, audit, /ready, restore Note every stumble | Light | Light | Remediation list clear or soft gate passed | "Phase B core controls are in place and I can defend them." | Ready for final hardening + Checkpoint 5
15-Oct-2026 | 45 | Thursday | Not Started | 10:00–11:00 — LangGraph state + reducers recall (UNDERSTAND) • Partial updates merge; what belongs in state vs config 11:00–12:00 — Security drill D-04 or D-09 practice (UNDERSTAND) • RAG prompt-only filter flaw OR approval race • Create → ship → discover → rollback → fix → regression gate | RAG prompt-only filter flaw Approval race | Blueprint §17 | PHASE B: Run one full security drill (D-04 RAG isolation or D-09 double-approve) • Create the flaw on a branch • Ship to staging • Discover via the detection signal • Roll back • Fix + add regression test • Keep test as gate Deliverable: drill write-up in docs/incidents/ or docs/drills/ | 16:15–17:00 Record the drill story (what I broke, how I found it, how I fixed it) 17:00–17:45 Link the drill back to the interview claim | More drill IDs (D-13 refresh reuse, D-14 fail-closed) — plan only | AWS: incident response basic | One complete drill loop finished | "I do not just claim security — I practise the create-ship-discover-rollback loop." | Drill muscle started
16-Oct-2026 | 46 | Friday | Not Started | 10:00–11:00 — agent_node vs tool_node recall (UNDERSTAND) • Only agent_node calls the LLM; tool_node never auto-runs sensitive 11:00–12:00 — Kill switch + feature flag deep dive (UNDERSTAND) • 30-second TTL cache on INVOKES_ENABLED • Flag must not be read once at import | Flag TTL cache No redeploy needed | Blueprint §8.5 | PHASE B: Feature flag polish + second drill • 30-second TTL cache on INVOKES_ENABLED • Test: flip flag → next request 503 within TTL • Run D-11 or D-14 style drill if time Deliverable: flag flip is observable without redeploy | 16:15–17:00 Record: bill-spike runbook (flip kill switch first) 17:00–17:45 Trap: flag is read once at import — how do you prevent that? | Observability: request_id correlation across logs + Langfuse + Sentry | AWS: cost anomaly detection idea | Kill switch reliable | "First action on a bill spike is flip the kill switch — no deploy required." | Ops controls strong
17-Oct-2026 | 47 | Saturday | Not Started | 10:00–11:00 — Loop protection + tool errors recall (UNDERSTAND) • Hard cap in state; safe terminal states 11:00–12:00 — Load model numbers (UNDERSTAND) • 50 users → ~10 concurrent invokes • What the probe entitles you to claim (honesty sentence) | 50 users → 10 concurrent invokes Why those numbers | Blueprint §0.1 §11.6 | PHASE B H10 light: The one load probe • Script or manual: 10–12 parallel invokes • Confirm 429s appear and provider mock never exceeds global cap • Write the exact sentence the probe entitles you to say Deliverable: load probe result + honesty sentence recorded | 16:15–17:00 Record the load-model paragraph 17:00–17:45 Honesty table review — what you will never claim | Multi-agent systems AWARE only (why Foreman stays single-agent supervisor) | AWS: what breaks first at higher traffic (LLM spend then PG connections) | Load probe done; honesty sentence written | "The probe entitles me to say we handle 10 concurrent invokes with back-pressure — not 50 concurrent LLM agents." | Honesty locked
18-Oct-2026 | 48 | Sunday | Not Started | 10:00–12:00 — Full HITL + approval integrity + CAS recall • interrupt → approve → resume • execute-once; owner re-check • Bypass questions: non-owner, expired, double-submit | interrupt → approve → resume execute-once owner re-check | Own graph + resume tests | BUFFER DAY • Strengthen any weak HITL tests • Second drill if energy (D-09 or D-21) • Checkpoint 5 evidence folder organised | 16:15–17:45 Defense: full pause-approve-resume vertical slice recorded (timed) Plus bypass questions (non-owner, expired, double-submit) | Light | Rest | HITL defense ≥4/5 | "I can narrate pause-approve-resume and the integrity controls cold." | HITL solid for Checkpoint 5
19-Oct-2026 | 49 | Monday | Not Started | 10:00–11:00 — Approval integrity + idempotency recall (UNDERSTAND) • Atomic UPDATE … WHERE status='pending' • Idempotency-Key on approve decision 11:00–12:00 — Demo gate full flow (UNDERSTAND) • demo_required / demo_expired • Quota on approve; unapproved never reaches provider | demo_required / demo_expired Quota on approve (Phase B side) | Blueprint §4.8 | PHASE B H13b: Demo gate completion • On approve: create/enable demo user + set low quota (25k tokens / $0.10) in one transaction • Approval email (mock or real adapter) • Expiry → 403 demo_expired, reads still work Deliverable: full demo request → approve → capped invoke works; unapproved still blocked | 16:15–17:00 Record complete demo-gate story 17:00–17:45 Trap: public URL with live keys — how is spend bounded? | UI copy honesty check (matches Blueprint) | AWS: public URL + WAF / rate-limit at edge (concept) | Demo gate fully production-ready | "The public link is open; the spending is not. Demo access is hand-approved, time-boxed and capped." | Demo gate closed
20-Oct-2026 | 50 | Tuesday | Not Started | 10:00–11:00 — Tool registry + prompt injection recall (UNDERSTAND) • Allowlist intersected after model output • Sensitive flag is code, not prompt 11:00–12:00 — Final IDOR + race matrix (UNDERSTAND) • All owned resources covered • Race tests for approve + invoke | Allowlist after generation Sensitive flag | Own tests | PHASE B: Final test hardening + remaining CI gates • All IDOR routes covered • Race tests for approve + invoke • Demo-gate test asserts zero provider calls for unapproved Deliverable: CI matrix matches Blueprint §11.2 critical rows | 16:15–17:00 Record: how prompt injection is stopped in code (not prompt) 17:00–17:45 Walk one race test | Who Types What final update for Phase B files | AWS: final architecture diagram | CI gates complete | "Allowlist is intersected after the model outputs tool calls — the prompt is not the control." | Test surface ready for Checkpoint 5
21-Oct-2026 | 51 | Wednesday | Not Started | 10:00–12:00 — CHECKPOINT 5 preparation — full architecture + all ADRs + Phase B controls • Public URL (demo gate on) serves full slice • Tests, drill write-ups, runbook, restore timing ready • Honesty table matches repo | Everything | ADR sheet + honesty table + drill write-ups | CHECKPOINT 5 PREP DAY • Public URL (demo gate on) serves full slice • Staging smoke + restore evidence ready • All critical tests green • Runbook + at least 2 drill write-ups • Honesty table matches repo | 16:15–17:45 Long recorded defense (15–20 min): architecture + HITL + Phase B controls + demo gate + honesty Log every weak spot | STAR stories final polish | Light | Evidence pack ready | "Checkpoint 5 is the industry bar — I can show the controls and the evidence." | Ready for Checkpoint 5
22-Oct-2026 | 52 | Thursday | Not Started | 10:00–11:00 — Gateway ADR + fallback recall (UNDERSTAND) • Hand-written vs LiteLLM • Error classification (what not to retry) 11:00–12:00 — Weak-spot remediation from yesterday • Only topics that scored ≤3 | Hand-written vs LiteLLM Error classification | Own ADR cards | Remediation + final polish only • Fix any Checkpoint 5 gaps • No new features | 16:15–17:45 Defense practice on weak spots only Re-record any 90s that scored ≤3 | Cost spike full scenario timed | AWS: final cost awareness paragraph | Weak spots closed or explicitly listed with reopen dates | "I own the gateway so I can explain fallback and metering." | Polish day
23-Oct-2026 | 53 | Friday | Not Started | 10:00–11:00 — Cost metering + kill switch recall (UNDERSTAND) • Spend-spike runbook: flip kill switch first 11:00–12:00 — Observability recall (UNDERSTAND) • request_id correlation across logs + Langfuse + Sentry • Logs vs traces — when you reach for each | Spend spike runbook Logs vs traces | Runbook + Langfuse | Final observability pass • request_id everywhere • Langfuse best-effort confirmed • Sentry tags confirmed Deliverable: one full invoke produces correlated log + trace + (if error) Sentry event | 16:15–17:00 Record full spend-spike response (flip kill switch → diagnose → prevent) 17:00–17:45 Record: how I debug a 4s RAG path | Model drift AWARE (why we do not claim it yet) | Light | Observability complete | "First action on spend spike is the kill switch. Then I look at usage_daily and the traces." | Ops story complete
24-Oct-2026 | 54 | Saturday | Not Started | 10:00–11:00 — Traces vs logs vs metrics (UNDERSTAND) • What each answers in an incident 11:00–12:00 — Final honesty table audit • What is mocked • Which sentences are true and which you will never claim | What is mocked What sentences are true | Blueprint §14b | HONESTY + README final • Update README and LinkedIn/CV claims to match exact repo state • Who Types What final • No over-claims on quotas, multi-agent, SOC 2, 50 concurrent agents, etc. Deliverable: public claims match repo | 16:15–17:45 Mock Interview A (architecture + HITL + Phase B controls) Record entire session. No notes. | "What would you do differently now?" 90s | STAR #1 and #2 timed | Mock A recorded; claims audited | "My public claims match what the repository actually contains." | Mock A done
25-Oct-2026 | 55 | Sunday | Not Started | 10:00–12:00 — Full system recall + all ADRs (light if energy low) • Only remediate Mock A weak spots if critical • No new topics | Everything | ADR cards + scorecard | BUFFER / rest day • Only remediate Mock A weak spots if critical • No new code | 16:15–17:45 Re-record any weak 90s from Mock A Light defense only | Rest | Rest | Energy protected; weak spots noted | Recovery day | Ready for final mocks
26-Oct-2026 | 56 | Monday | Not Started | 10:00–11:00 — Deploy story + App Runner vs ECS vs Lambda (UNDERSTAND) • What breaks first at higher traffic 11:00–12:00 — Demo gate + public URL story (UNDERSTAND) • How spend is bounded on the public link | What breaks first at load Demo gate bounds spend | ADR-007 + §4.8 | Final deploy verification • Public URL healthy • Demo gate on • Staging and prod parity still true • Rollback path documented | 16:15–17:45 Mock Interview B (full attack: auth, HITL, RAG isolation, cost spike, demo gate, 'Did AI write this?') Record everything | 90s: Did AI write this? — name HAND-TYPED files | Final STAR polish | Mock B recorded | "I can defend the full system including the Phase B controls under interruption." | Mock B done
27-Oct-2026 | 57 | Tuesday | Not Started | 10:00–12:00 — ADR fire-round (all decisions that exist in code) • Every ADR card: context · decision · rejected alternative · why • Only defend what is actually in the repository | Every ADR card | Own cards | No new features • Only claim audit and weak-spot list with owners and reopen dates | 16:15–17:45 Defense: interviewer picks random ADRs + Phase B controls Record | Final claims register tick | Light | Weak-spot list with owners exists | "I only defend decisions that are actually in the repository." | ADR defense solid
28-Oct-2026 | 58 | Wednesday | Not Started | 10:00–12:00 — Final Checkpoint 5 style review • Full evidence pack walk-through from memory • Architecture + HITL + Phase B controls + honesty | Full evidence pack | All previous | CHECKPOINT 5 (Industry bar) • Demonstrate full slice on public URL (demo gate on) • Show tests, drill write-ups, runbook, restore timing • Confirm honesty table • Record the session | 16:15–17:45 Continuous defense take covering architecture + Phase B + honesty This is the final gate recording | Rest after | Rest | Checkpoint 5 passed or explicit remaining debt listed | "The system is at the industry bar I claimed — controls, evidence, and honesty." | Checkpoint 5 done
29-Oct-2026 | 59 | Thursday | Not Started | 10:00–12:00 — Weak-spot remediation only (from Checkpoint 5 + mocks) • Only remaining 3s • Fix the named debt items; re-test | Only remaining 3s | Scorecard | Remediation only — no new scope • Fix the named debt items • Re-test | 16:15–17:45 Final weak-spot recordings Then stop | Light STAR | Light | All critical debt closed or accepted with date | Clean close | Ready for Day 60
30-Oct-2026 | 60 | Friday | Not Started | 10:00–11:00 — Final self-audit against Blueprint consistency check • Honesty + evidence 11:00–12:00 — Rest or light review • No new topics; close cleanly | Honesty + evidence | Blueprint §21 + §14b | CLOSE PHASE B • Final README • Final Who Types What • Final claims register • Weak-spot list with owners • No new features • Celebrate the 60-day finish | 16:15–17:00 Optional light mock or rest 17:00–17:45 Applications planning + interview calendar | Rest | Rest | 60-day project closed cleanly; Phase A + Phase B complete; defense recordings exist | "I spent 60 days building and hardening something I can actually defend at the industry bar." | Project complete
LEGEND: Blue-tint cells = Phase B build work ¦ Yellow = Checkpoint / soft gate days ¦ Green = Buffer / recall days ¦ Orange = Mock interview days. Slot structure identical to Days 1–30. Goal = finish full 50-user Industry Blueprint + be able to strongly defend both Phase A and Phase B.